## Sheet1
Reference Number | Type | Status | Submited By | Date Submited | Owner | Details | Solution
1 | Feature | Fixed | Burt | 2013-11-04 | Benjamin | Validate data on leaves: want to validate the input in the leaves | For the moment changed the event ref for a typdef in case we add the other object
2 | Feature | Fixed | Jack | 2013-11-04 | Benjamin | Detach the claqss from the menu. I want a way to decouple the shortcut menu/tree item name and the name of the instance class
3 | Bug | Fixed | Jack | 2013-11-03 | Benjamin | SaveFlag state variable should have a better name..."UnsavedChanges" | Renamed Control
4 | Bug | Fixed | Jack | 2013-11-03 | Benjamin | what is the "s" variable in the duplicate channel VI? | Renamed Control
5 | Bug | Fixed | Jack | 2013-11-03 | Benjamin | Data Acces is misspelled in repo | Fixed typo
6 | Feature | Rejected | Chris | 2013-11-03 | Benjamin | It would be nice to have buttons on the main configurator for common operations like Open and Save. | The functions are on the file menu, should we also add the buttons? In the duke add we had them but they ended removing them as they added other buttons.
7 | Bug | Fixed | Chris | 2013-11-03 | Benjamin | The multiple channel editor doesn't have a "Panel Close?" event, which causes the main UI to hang if I close the multi channel editor window with the X button.
8 | Bug | Fixed | Chris | 2013-11-03 | Benjamin | The UI layout of the multiple channel editor isn't very clean. The OK and Cancel buttons should be near the bottom right of the window, and the empty space around the controls should be uniform.
9 | Bug | Fixed | Chris | 2013-11-03 | Benjamin | When I close the UI, it clears the subpanel before bringing up the confirmation dialog. It should clear the subpanel only after it is certain that the program is exiting.
10 | Bug | FIxed | Chris | 2013-11-03 | Benjamin | VIs should be saved near the upper left corner of the screen. A lot of the VIs here are saved partially on the second monitor, and it's really annoying to have to drag every window over when using one monitor.
11 | Bug | FIxed | Chris | 2013-11-03 | Benjamin | Avoid using carriage returns in free labels.
12 | Bug | Rejected | Chris | 2013-11-03 | Benjamin | All VIs should have automatic error handling turned off. You should turn off the "Enable automatic error handling in new VIs" setting in Tools >> Options >> Block Diagram. | Not sure about this one, if its not a finished program having this on helps finding the un-handled errors? shouldn't we leave it on?
13 | Bug | In Work | Chris | 2013-11-03 | Benjamin | The VIs in Configurator.lvlib are missing context help descriptions
14 | Bug | In Work | Chris | 2013-11-03 | Benjamin | Sub VI input terminals should be "Required", unless they are meant to run correctly with nothing wired. Most of the VIs in this projects use non-required inputs. You should turn on the "Connector pane terminals default to Required" setting in Tools >> Options >> Front Panel.
15 | Bug | Fixed | Chris | 2013-11-03 | Benjamin | Configurator_Main.vi has an unwired shift register passing the error cluster. If there is an error in the "Exit" case, then the VI won't run properly the next time it is called. As a good practice, the error wire from Create Message Queue. | Fixed the unitiliazed shift register. and yes most errors on top loop are being ignored or forwarded down to the Error case on the consumer. The consumer can stop top loop in case of an error.
16 | Bug | Fixed | Chris | 2013-11-03 | Benjamin | GenerateFlatInformation.vi is broken. | Removed Vi
17 | Bug | Fixed | Chris | 2013-11-03 | Benjamin | Control labels should not be spelled in CamelCase. For consistency, they should use lower case with spaces. | all is lower cases except names, names are still camel case (SLB)
18 | Feature | In Work | Chris | 2013-11-13 | Benjamin | In the VIP build spec, you should fill out the "Product Description Summary" and "Product Description" fields to give users an idea of what the framework actually does.
19 | Bug | Fixed | Chris | 2013-11-13 | Benjamin | Would it make more sense for the product name to be "Configuration Editor Framework"?
20 | Bug | Fixed | Chris | 2013-11-13 | Benjamin | There shouldn't be a Controls palette.
21 | Bug | Fixed | Chris | 2013-11-13 | Benjamin | Palettes should not be on the root palette. See the VIP Style Guidelines for where to place the palette. Addons would probably be the best place for this.
22 | Bug | Fixed | Chris | 2013-11-13 | Benjamin | The Functions palette should not just mirror the file hierarchy. None of the files in the ProjectTemplates folder belong in the palettes, and only a subset of the vi.lib VIs should be in there.
23 | Feature | Fixed | Chris | 2013-11-13 | Benjamin | Subpalettes should have nicer looking icons.
24 | Bug | Fixed | Chris | 2013-11-13 | Benjamin | In the template project, the framework libraries (Node, Repository, TreeControl) are in the project without any indication that they should not be modified by users. It might be good to add a text file to this virtual folder that says not to modify any of this code. In fact, TreeControl.lvlib doesn't need to be here at all because it doesn't contain any methods that need to be overridden, and whatever reusable VIs it does contain should be in the palette.
25 | Bug | Fixed | Chris | 2013-11-13 | Benjamin | Some of the VIs still have auto error handling enabled. | Found 2 Vis with that and changed them
26 | Bug | Fixed | Chris | 2013-11-13 | Benjamin | Some of the VIs don't have icons.
27 | Bug | Rejected | Chris | 2013-11-13 | Benjamin | Many VIs still have non-required input terminals. | Duplicated, Still working on this
28 | Feature | Fixed | Benjamin | 2013-11-13 | benjamin | Move link and unlink back into node library
29 | Bug | Fixed | Julianne | 2013-11-19 | Benjamin | In cRIO.lvclass:CRIOUI.vi, "Refeshnode" should be "RefreshNode" (capitalize the N). Incorrect capitalization causes an AMC error to be thrown. | Fixed on the 11/18 build shloudl be there in rev 15
30 | Feature | in work | Julianne | 2013-11-19 | Benjamin | Add comments/documentation that clearly explains that the Call Parent Node function must be called in the overridden To Repo function to maintain the recursive list.
31 | Feature | fixed | Burt | 2013-12-02 | Benjamin | Allow different folder structure for clases
32 | Feature | in work | Jack | 2013-12-03 | Benjamin | Add project specification
33 | Feature | Fixed | Benjamin |  |  | Add documentation to the VIs in the example from the getting started guide
34 | Feature | Fixed | Benjamin |  | Benjamin | take the to tre and from tree outside the open and save vis.
35 |  |  | Chris |  | Benjamin | The glyph used in the product icon is a picture of a wheel, not a gear. I would replace this glyph with the actual gear icon you use in other places. Same thing for the palette icon. The banner isn't really needed here either.
36 | [5 empty] | The "Product Homepage (URL)" and "Product Description Summary" fields should be filled out. I think you can save a document in Vignette as a draft to get the URL before publishing it.
37 | [5 empty] | I would change the Product Description to something more descriptive. This package doesn't actually include any tools, so avoid using that word. Maybe something like:
38 | [5 empty] | Framework for creating configuration editors. The included classes can be extended to create custom configuration hierarchies.
39 | Bug | In Work | Aaron Gelfand | 2014-08-13 | Benjamin | cRIORepo Class has default class icon rather than a specific icon
40 | Feature | In Work | Aaron Gelfand | 2014-08-14 | Benjamin | Add hashtags showing where to replace class constants for use in customer's Configurato_Main.vi
41 | Feature | Rejected | Aaron Gelfand | 2014-08-15 | Benjamin | Consider adding a general purpose Save in parent class Repo (Save.vi in NISE_CEF_Repository) rather than NO-OP
42 | Feature | Rejected | Aaron Gelfand | 2014-08-16 | Benjamin | Consider rename cRIO.lvclass as cRIO_Root.lvclass to help define what its relationship is
43 | Bug | In Work | Aaron Gelfand | 2014-08-17 | Benjamin | Typo in VI Description of ..vi.lib\CEF_TreeControl\Summary.vi
44 | Bug | In Work | Aaron Gelfand | 2014-08-18 | Benjamin | ..vi.lib\CEF_TreeControl\GlyphIndexPairs.vi enum control should be labeled as Action rather than Enum
45 | Feature | In Work | Aaron Gelfand | 2014-08-19 | Benjamin | Better documentation on what folder glyphs should be located in (or an option to allow path to be specified for all glyphs in a repo)
46 | Feature | In Work | Aaron Gelfand | 2014-08-20 | Benjamin | Documentation should state the folder name of the node classes must exactly match the class name (had a problem when my folder was named ResistorTests but class was ResistorTest
47 | Feature | defered | Aaron Gelfand | 2014-08-21 | Benjamin | Since UI's are not an override method (although UIRef.vi is), a template with the correctly named controls should be provided, especially since the framework appears to set the controls programmatically
48 | Feature | In Work | Aaron Gelfand | 2014-08-22 | Benjamin | A hashtag or other documentation showing a user how to create/replace the DVR typecasting constant in the VI would be useful.
49 | bug | in work | Aaron Gelfand |  |  | Error clusters in the In Place Element structures not wired, resulting in pop-ups. | Getting Adition information
50 | bug | in work | Aaron Gelfand |  |  | Typo in VI description in ..Source\CEF Test\subVI\FileDialog.vi